## Risk Register
RISK REGISTER
ID | Risk Name | Date Raised | Risk & Impact Description | Likelihood | Consequences | Overall | Proposed Mitigation | Owner | Target Date to Resolve | Status
1 | Accidental deletion of project. |  | Project files such as gantt chart, diagrams and codes may be lost due to accidental deletion or unintentional wipe out of files by changing system settings etc. | Possible | Moderate | High | Back up every version of file after every save or edit onto GitHub. | Fairuz |  | open
2 | Laptop cannot startup during lockdown or after lockdown is lifted. |  | Laptop cannot be turned on for no particular reason. | Possible | Moderate | High | Back up every version of file after every save or edit onto GitHub. Contact Lei or Simon about it. Rent a laptop from Unitec. If this is not possible, To purchase a new laptop asap. | Fairuz |  | open
3 | House catches fire. |  | Cannot complete project in time because of a house fire. | Possible | Catastrophic | Extreme | Contact Lei or Simon about it. Rent a laptop from Unitec. If it is still possible to work on project, purchase a new laptop asap. | Fairuz |  | open

## Issues Register
ISSUES REGISTER
ID | Date Raised | Project | Issue Title | Issue Description | Specific Deliverable/Milestone affected | Likelihood | Consequences | Overall Issue Rating | Proposed Resolution / Mitigating Action | Issue Owner | Target Date to Resolve | Progress Status / Commentary | Open / Closed

## Risk Matrix
Unitec RISK FRAMEWORK
Likelihood/Impact | Insignificant | Minor | Moderate | Major | Catastrophic
Almost Certain | Moderate | High | High | Extreme | Extreme
Likely | Moderate | Moderate | High | Extreme | Extreme
Possible | Low | Moderate | High | High | Extreme
Unlikely | Low | Low | Moderate | High | High
Rare | Low | Low | Moderate | Moderate | High

## Data (hidden)
Likelihood | Consequences
Almost Certain | Insignificant
Likely | Minor
Possible | Moderate
Unlikely | Major
Rare | Catastrophic